|  | Project Brief: Twainy Plast Sanitary From Visitors to Customers: A Social Media & Digital Growth Strategy MKT 843 Strategic Social Media Management · Dr. Kiray Khoury · LAU AKSOB MBA · Submitted October 22, 2026 · Team: [names] |
| --- | --- |

1. Client overview

Twainy Plast Sanitary is a family-run Lebanese retailer and wholesaler of sanitary ware and plumbing products, located in [town / district]. It sells 175 products (mixers and faucets, LED mirrors, WCs, basins and vanities, showers, floor drains and water pumps, mostly $5–$250) to homeowners renovating bathrooms and kitchens, and to plumbers and small contractors. In October 2026 the business launched its online store, twainyplast.com (Shopify), but it has no structured social media or digital marketing strategy yet. That makes it a digitally underdeveloped local enterprise as defined in the brief.

2. The business problem

People are visiting the new website, but nobody is buying. Shopify Analytics for the first days after launch shows:

| Sessions, launch week | Add-to-cart rate | Completed orders | Traffic from social media |
| --- | --- | --- | --- |
| 252 | 1.1% (3 of 270 sessions) | 0 (1 checkout started) | 6% (91% direct links) |

Only 44% of sessions come from Lebanon, and most people leave before adding anything to the cart. Our first audit points to possible barriers: social channels are not active, product images are renders rather than real photos, delivery and payment terms are only shown at checkout, and the home page invites visitors to "Our Journey" rather than to shop. With this little data these are hypotheses, to be confirmed through research before they are treated as causes.

Research question: How can Twainy Plast use targeted social content, customer trust and an easier buying journey to turn website visitors into paying customers?

3. The project idea: "Choose with Confidence: اختار بثقة"

Shoppers hesitate to buy bathroom and plumbing products online because they cannot check fit, quality or delivery. Our idea is to position Twainy Plast as the clear, honest local expert that helps people choose the right product and makes buying simple. The 4-week social campaign will focus on a small set of well-stocked, clearly priced products (Brax mixers at $25–65 and LED mirrors at $40–60) and run on four content pillars:

- Choose Right: fit and size guides and product comparisons (e.g., "3 things to check before buying a mixer").

- Inside Twainy: the real store, family and team, plus packing and delivery, to build trust.

- Real Homes: genuine customer reviews and installed projects, used only with consent.

- Order Easy: clear prices, delivery and payment terms, and an honest offer with real end dates.

Channels: Instagram and Facebook for discovery and ads, WhatsApp Business for advice and quotes, Google Business Profile for local search, and the website for checkout. The two target personas are Rania, a homeowner renovating her bathroom (goal: buy online), and Hassan, a plumber or small contractor (goal: request a quote on WhatsApp).

4. Objectives

Main objective: build a measurable path from social media attention to paying customers, moving Twainy Plast from 0 online orders to a tested, repeatable sales engine within a 4-week campaign (Oct 29 – Nov 25, 2026).

| Objective | 4-week target | Baseline today |
| --- | --- | --- |
| Convert | 10 online orders + 8 WhatsApp-assisted orders; website conversion rate 1% | 0 orders; 0% conversion |
| Attract | 1,000 sessions from Lebanon via campaign links; add-to-cart rate 4% | 120 Lebanon sessions in 14 days; 1.1% add to cart |
| Engage | 25,000 reach in Lebanon; engagement rate ≥ 3% of reach; link CTR ≥ 1% | No active social presence |
| Trust & measure | GA4 + Meta Pixel live; 10 genuine Google reviews; reply time < 1 hour; CAC ≤ $20 on a $200 ad test | No tracking; 0 reviews |

These are test targets, not forecasts; they will be revised after week 1. Course fit: data-driven problem solving (CLO 1), team agency workflow (CLO 2), ethical targeting, privacy and honest offers (CLO 3), and an executive pitch (CLO 4).

5. Roadmap

| Phase | Dates | Key activities | Deliverable |
| --- | --- | --- | --- |
| 0 · Prepare | Oct 22 – 28 | Submit brief and owner consent; audit 3 competitors (Builders Sal, Arcom Group, Chromotech); 10–12 customer and plumber interviews; mobile test order; real product photos; delivery and payment info on product pages; GA4, Pixel and UTM set-up | Validated personas, competitor audit, a store ready to sell |
| 1 · Trust & choice | Oct 29 – Nov 11 | Brand identity and profile set-up; Reel 1 (meet the store) and Reel 2 (mixer fit guide); guide carousels; Google Business Profile launch; $100 A/B ad test | Engaged audience, winning ad creative |
| 2 · Convert & prove | Nov 12 – 25 | Offer post and Reel 3 (from click to your door); scale the winning ad and retarget ($100); customer story; review requests; weekly optimisation every Wednesday | First orders, reviews, measured CAC and ROAS |
| 3 · Measure & present | Nov 25 – Dec 3 | Compare results with the launch baseline; ROI model; recommendations; final strategy deck | Executive presentation (Nov 26 / Dec 3) |

6. Deliverables

- Strategic Digital Transformation Deck covering Steps 1–5: competitor social audit, 2 personas, brand identity matrix, channel architecture and profile mockups.

- 4-week cross-platform content calendar with posting times, captions (Arabic and English), hashtags and calls to action.

- Creative assets: 3 Reels or high-fidelity storyboards and 5 static posts or carousels.

- KPI framework and ROI model (reach, engagement rate, CTR, CAC, ROAS, conversions), tracked in Meta Business Suite, GA4 and Shopify, with before and after results.

- A 15–20 minute executive presentation on November 26 or December 3, 2026.

7. Ethics and client consent

The team will use customer data only with consent (cookie banner, opt-in WhatsApp lists, anonymised interviews), publish no fake reviews or misleading discounts, target ads by location only (never by religion, politics or other sensitive traits), and confirm every price and claim with the owner before posting. The project scope has been explained to the owner, whose signature below authorises the audit, the creative work and the presentation of results. Publishing any post or spending any ad budget requires the owner’s prior written approval.

Owner / Manager: ____________________   Signature: ____________________   Date: ________        Team representative: ____________________